## Omnichannel Dev Cost
Omnichannel Inventory Management system development
Estimated project completed in 8-12 months
Consider BA Squad team member working for 8 hours a day, 5 days in a week | 40 hours/week | 160 hours/month | 1120
How many developers and testers worked on project
1. Labor Estimate information | Units/Hrs. | Cost/Unit/Hr | Subtotals | Calculations
BA Squad Project Team Member Estimate
Project Manager | 1120 | 44.43 | 49761.6 | 1120*44.43
Team Lead | 1120 | 23.33 | 26129.6 | 1120*23.33
7 Business Analysts | 7840 | 40.7 | 319088 | 7840*40.70
Contractors Labor Estimate
2 Developer | 2240 | 40.55 | 90832 | 2240*40.55
Test Lead | 1120 | 50.95 | 57064 | 1120*50.95
2 Tester | 2240 | 33.75 | 75600 | 2240*33.75
Total Labor Cost Estimate | 15680 | 233.71 | 618475.2

## EstimatedBudget
The Estimate: Omnichannel Inventory Management Project Cost Baseline | [6 empty] | A definitive estimate: -5 percent to +10 percent
| Units/Hrs. | Cost/Unit/Hr | CCA Cost(Class 10, 30%) | Subtotals | Year 1 Total | Year 2 Total
1. Project Management
1.1 Project Manager | 1120 | 44.43 |  | 49761.6 | 4726155.2
1.2 Team Lead | 1120 | 23.33 |  | 26129.6
1.3 7 Business Analysts | 7840 | 40.7 |  | 319088
1.4 BA SQUAD Consulting Charges | - | $ |  | 3000000
1.4 Contract(Software development and Testing) | 5600 | 237.71 |  | 1331176
2. Hardware
2.1 Handheld Devices | 10 | 10000 | 54000 | 100000 | 180000 | 54000
2.2 Cloud/Servers | 2 | 40000 |  | 80000
3. Software
3.1 Licensed Software | 3 | 15000 | 73500 | 45000 | 245000 | 73500
3.2 Software Development* |  |  |  | 200000
4. Testing |  |  |  | 69600 | 69600
5. Training and Support
5.1 Trainee Cost | 100 | 1000 | 87803.04 | 100000 | 292676.8 | 87803.04
5.2 Travel Cost | 10 | 1500 |  | 15000
5.3 Project Team Members | 1680 | 105.76 |  | 177676.8
Subtotal |  |  |  | 5513432 |  | 215303.04
Total Claim Amount |  |  | 215303.04
Total Project Cost Estimate |  |  |  | 5513432 | 5513432 | 215303.04

## ROI
ROI Calculation
Initial Investment | 5513432 |  | Yearly Expenses | 1170703.04
Income Tax Rate | 25%
Year -1 | [5 empty] | Year -1 | Year - 3 | Year - 5 | Year - 10 | Year - 15
Customers |  | Target Revnue | Total
1000000 | 0 | 1 Month | 0 |  | Income Before Taxes | -5513432 | 7829296.96 | 10829296.96 | 22829296.96 | 34829296.96
1000000 | 0 | 1 Year | 0 |  | Income Taxes | -1378358 | 1957324.24 | 2707324.24 | 5707324.24 | 8707324.24
[5 empty] | Net Income | -4135074 | 5871972.72 | 8121972.72 | 17121972.72 | 26121972.72
Year - 3
Customers |  | Target Revnue | Total |  | ROI | -75% | 501.6% | 693.8% | 1463% | 2231%
1500000 | 0.5 | 1 Month | 750000
1500000 | 6 | 1 Year | 9000000
Year - 5 |  |  |  |  | Cumulative Net Profit | 53102816.88
Customers |  | Target Revnue | Total
2000000 | 0.5 | 1 Month | 1000000
2000000 | 6 | 1 Year | 12000000
Year - 10
Customers |  | Target Revnue | Total
4000000 | 0.5 | 1 Month | 2000000
4000000 | 6 | 1 Year | 24000000
Year - 15
Customers |  | Target Revnue | Total
6000000 | 0.5 | 1 Month | 3000000
6000000 | 6 | 1 Year | 36000000